## Factory
Factory Fabrication Installation Cost Calculator - August 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Factory Fabrication Installation Cost Estimating - Large Panels
| Area | 100000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g. range 0.75 (all slope) to 1.25 (all flat)
| Roll Width | 22.5 | e.g. for 40 mil reinforced FML
| Roll Length | 560 | e.g. for 40 mil reinforced FML
| Number of Rolls | 7.9365 | e.g. for 40 mil reinforced FML
| Feet of Basic Seam | 4444.4444 | net lined area divided by roll width
| Feet of Cross Seam | 178.5714 | basic seam length divided by roll length
| Total Seam length | 4623.0159 | total seam length (need to check panel layout)
| Length of Tie-in Seam | 1000 | e.g. welded connection to exisiting liner
| Ave Seam Speed | 20 | assumed speed of primary seam wedge welder per minute
| Hours per Day | 8 | hours per work day on site
| Extra Hours per Day | 2 | extra hours per work day on site
| Set Up Time | 1 | i.e. basic no. days for factory production set up, ranging from 1 to 2 days depending on the length of the project
| Seaming Time | 1.1715 | i.e. basic no. days for factory production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 0.24802 | i.e. days to deploy & ballast geomembrane rolls (assumes 0.25 hour per roll)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1 | i.e. added days for detail work
| Total Days on Site | 2.4195 | i.e. assumes QC included |  |  |  | i.e. | 365.5529 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e. mobilization charge |  |  |  | i.e. | 0.94883 | acres per day
| Training Days Pre-Start | 0 | e.g. site specific safety training |  |  |  | i.e. | 2.4195 | days on site
| Days Total | 3.4195 | i.e. assumes QC included
| Non-Work Days | 2 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
|  |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 1641.3492 | non-union | 27.3558
| QC Tech | 1 | 50 | 1367.791 | non-union | 27.3558
| Welding Techs | 2 | 40 | 2188.4656 | non-union | 54.7116
| Laborers | 4 | 20 | 2188.4656 | non-union | 109.4233
| Extra Hours |  | Unit Cost | Cost
| Supervisor | 1 | 90 | 615.506 | non-union | 6.839
| QC Tech | 1 | 75 | 512.9216 | non-union | 6.839
| Welding Techs | 2 | 60 | 820.6746 | non-union | 13.6779
| Laborers | 4 | 30 | 820.6746 | non-union | 27.3558
|  |  |  | Cost |  | Cost
| Labor Total (Crew Size) | 8 |  | 7386.0714 | non-union | 273.5582 | i.e. | 27 | av. cost of labor per man hour
| Trucks | 3 | 30 | 2462.0238 | i.e. charge out rate
| Generators | 2 | 20 | 1094.2328 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 1094.2328 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 2188.4656 | i.e. charge out rate
| Large loader | 1 | 30 | 820.6746 | i.e. charge out rate
| Small loader | 1 | 20 | 547.1164 | i.e. charge out rate
| Equipment Total | 13 |  | 8206.746 | i.e. charge out rate |  | i.e. | 2400 | per day for equipment
| Hotel rooms | 5 | 120 | 2051.6865
| Per diems | 8 | 40 | 1094.2328
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 2 | 100 | 200
| Factory Project Total Cost |  |  | 24738.7368 |  |  | i.e. | 0.24739 | per sq. ft.
Does not include costs for materials.
Add Legal disclaimer regarding liability from liquidated damages. "For estimating purposes only … Owens Corning not responsible for …"

## Field
Field Fabrication Installation Cost Calculator - May 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Input Parameters
Calculated
Field Fabrication Installation Cost Estimating - Rolled Goods
| Area | 100000 | square feet, net lined area
| Deployment/shape factor | 1 | e.g. range 0.75 (all slope) to 1.25 (all flat)
| Roll Width | 22.5 | e.g. for 60 mil HDPE geomembrane
| Roll Length | 560 | e.g. for 60 mil HDPE geomembrane
| Number of Rolls | 7.9365 | e.g. for 60 mil HDPE geomembrane
| Feet of Basic Seam | 4444.4444 | net lined area divided by roll width
| Feet of Cross Seam | 178.5714 | basic seam length divided by roll length
| Total Seam length | 4623.0159 | total seam length (need to check panel layout)
| Length of Tie-in Seam | 1000 | e.g. welded connection to exisiting liner
| Ave Seam Speed | 22 | assumed speed of primary seam wedge welder per minute
| Hours per Day | 8 | hours per work day on site
| Extra Hours per Day | 2 | extra hours per work day on site
| Set Up Time | 2 | i.e. basic no. days for field production set up, ranging from 2 to 3 days depending on the length of the project
| Seaming Time | 1.065 | i.e. basic no. days for field production seaming assuming standard QC & 50% actual welding time
| Deployment Time | 0.24802 | i.e. days to deploy & ballast geomembrane rolls (assumes 0.25 hour per roll)
| Number of Details | 8 | pipe pentrations
| Time per Detail | 1 | hours
| Details Time | 1 | i.e. added days for detail work
| Total Days on Site | 4.313 | i.e. assumes QC included |  |  |  | i.e. | 289.8227 | sq-ft / man-hour
| Travel Time to Site | 0 | i.e. mobilization charge |  |  |  | i.e. | 0.53227 | acres per day
| Training Days Pre-Start | 0 | e.g. site specific safety training |  |  |  | i.e. | 4.313 | days on site
| Days Total | 4.313 | i.e. assumes QC included
| Non-Work Days | 3 | Sundays and rain/weather delays. Depending on duration of project and location, this ranges from 2-5
|  |  | Unit Cost | Cost |  | Man-hours
| Supervisor | 1 | 60 | 2070.2309 | non-union | 34.5038
| QC Tech | 1 | 50 | 1725.1924 | non-union | 34.5038
| Welding Techs | 2 | 40 | 2760.3078 | non-union | 69.0077
| Laborers | 4 | 20 | 2760.3078 | non-union | 138.0154
| Extra Hours |  | Unit Cost | Cost |  | Extra man-hours
| Supervisor | 1 | 90 | 776.3366 | non-union | 8.626
| QC Tech | 1 | 75 | 646.9472 | non-union | 8.626
| Welding Techs | 2 | 60 | 1035.1154 | non-union | 17.2519
| Laborers | 4 | 30 | 1035.1154 | non-union | 34.5038
|  |  |  | Cost |  | Cost
| Labor Total (Crew Size) | 8 |  | 12809.5536 | non-union | 345.0385 | i.e. | 37.125 | av. cost of labor per man hour
| Trucks | 3 | 30 | 3105.3463 | i.e. charge out rate
| Generators | 2 | 20 | 1380.1539 | i.e. charge out rate
| Fuel | 0 | 20 | 0 | i.e. charge out rate
| Wedge Welders | 2 | 20 | 1380.1539 | i.e. charge out rate
| Other Tools & Equipment | 4 | 20 | 2760.3078 | i.e. charge out rate
| Large loader | 1 | 30 | 1035.1154 | i.e. charge out rate
| Small loader | 1 | 20 | 690.077 | i.e. charge out rate
| Equipment Total | 13 |  | 10351.1544 | i.e. charge out rate |  | i.e. | 2400 | per day for equipment
| Hotel rooms | 5 | 120 | 2587.7886
| Per diems | 8 | 40 | 1380.1539
| Mobilization | 8 | 750 | 6000
| Non-Work Day Expenses | 3 | 100 | 300
| Field Project Total Cost |  |  | 33428.6505 |  |  | i.e. | 0.33429 | per sq. ft.
Does not include costs for materials.
Add Legal disclaimer regarding liability from liquidated damages. "For estimating purposes only … Owens Corning not responsible for …"

## Comparative Sheet
Deployment methods comparisons - August 2020
By: Timothy D. Stark, Ph.D., P.E., D.GE, F.ASCE
Fabricated Geomembrane Institute
University of Illinios at Urbana-Champaign
Cost comparison
|  | Field | Factory
Cost
| Labor Total (Crew Size) | 12809.5536 | 7386.0714
| Equipment Total | 10351.1544 | 8206.746
| Hotel rooms | 2587.7886 | 2051.6865
| Per diems | 1380.1539 | 1094.2328
| Mobilization | 6000 | 6000
| Non-Work Day Expenses | 300 | 200
| Project Total Cost | 33428.6505 | 24738.7368
If choosing factory fabricated pannels for deployment, total savings will be:
8689.9137
Time comparison
|  | Field | Factory
Time (days)
| Days total | 4.313 | 3.4195
| Non work days | 3 | 2
If choosing factory fabricated pannels for deployment, the time saved is:
|  |  | 1.8935 | days