## Simple matrix
Simple Matrix
Communication | Method | Frequency | Goal | Owner | Audience
Project status report | Email | Weekly | Review project status and discuss potential issues or delays | Project manager | Project team + project sponsor
Team standup | Meeting | Daily | Discuss what each team member did yesterday, what they'll do today, and any blockers | Project manager | Project team
Project review | Meeting | At milestones | Present project deliverables, gather feedback, and discuss next steps | Project manager | Project team + project sponsor
Post-mortem meeting | Meeting | At end of project | Assess what did and did not work and discuss actionable takeaways | Project manager | Project team
Task progress updates | TeamGantt | Daily | Share daily progress made on project tasks | Project manager | Project team

## By channel
By Channel
Communication | Frequency | Goal | Owner | Audience
Email
Project status report | Weekly | Review project status and discuss potential issues or delays | Project manager | Project team + project sponsor
Meetings
Team standup | Daily | Discuss what each team member did yesterday, what they'll do today, and any blockers | Project manager | Project team
Project review | At milestones | Present project deliverables, gather feedback, and discuss next steps | Project manager | Project team + project sponsor
Post-mortem meeting | At end of project | Assess what did and did not work and discuss actionable takeaways | Project manager | Project team
TeamGantt
Task progress updates | Daily | Share daily progress made on project tasks | Project manager | Project team

## By audience
By Audience
Communication | Frequency | Goal | Owner | Method
Project team
Project status report | Weekly | Review project status and discuss potential issues or delays | Project manager | Email/Meeting
Team standup | Daily | Discuss what each team member did yesterday, what they'll do today, and any blockers | Project manager | Meeting
Task progress updates | Daily | Share daily progress made on project tasks | Project manager | TeamGantt
Project review | At milestones | Present project deliverables, gather feedback, and discuss next steps | Project manager | Meeting
Post-mortem meeting | At end of project | Assess what did and did not work and discuss actionable takeaways | Project manager | Meeting
Project sponsor
Project status report | Weekly | Review project status and discuss potential issues or delays | Project manager | Email/Meeting
Project review | At milestones | Present project deliverables, gather feedback, and discuss next steps | Project manager | Meeting