## Pillar OPRA Test Plan - May 22
Pillar OPRA - Testing Checklist
Participant/Subscriber:
Contact Name:
Contact Email:
Contact Phone#:
# | Time | Test Category | Action By | Test Description | Expected Results | Tested? ( Y, N, N/A ) | Participant Comments
Hourly Test Script
1 | 1:30 |  | OPRA | Pillar OPRA to trigger Start of Day message
2 | 1:30:00 - 9:30:00 AM |  | Participants | Participants to establish connectivity for Primary Input IP/Ports on Pillar OPRA Note - Participants must also connect to Legacy OPRA | Participants to establish connection on Primary Lines
|  |  | Participants | Participants can start to submit Extended Hours Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
3 | 9:30 |  |  | Market Open
4 | 9:30:00 - 9:45:00 AM | Single Participant Line Disconnect | Participants | All Participants to start submitting Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
|  |  | OPRA | Pillar OPRA to simulate Input Port failure of a subset of OPRA Input lines for each participant | Participant will see some Primary input lines disconnected
|  |  | Participants | For the affected lines, Participants to reconnect to OPRA on their backup lines and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence number via Block Sequence Number Status Response Message (Category N Type M)
|  |  |  | Participants to start submitting Quote and Trade data via their backup connections | Quotes and trades accepted and disseminated on the output lines
5 | 9:45:00 - 10:15:00 AM | Individual Participant Input failover to DR (Optional Test) | Participants | Participant to request OPRA to enable their Input lines on DR site
|  |  | OPRA | Pillar OPRA to disable respective Participant's Input lines on the Production site and enable the Input lines on the DR site | Participant will see Production input lines disconnected and can no longer reconnect to Production Input lines
|  |  | Participants | Participants to reconnect to OPRA on their DR Input lines and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message | OPRA to accept input connections and respond with latest sequence number, as previously processed on the Production site for the corresponding Input line, via Block Sequence Number Status Response Message
|  |  |  | Participants to start submitting Quote and Trade data via their DR connections | Quotes and trades accepted and disseminated on the output lines
6 | 10:15:00 - 10:30:00 AM | Partial site Failover from Production to DR for output Multicast lines | OPRA | Pillar OPRA to simulate partial failure of Output Publication process which will disrupt data flow for a subset of multicast output lines | - No impact to input participants, they shall continue to send messages on the input lines on which they are connected to - Subscribers would see an outage in data flow on the affected output lines
|  |  |  | Pillar OPRA to switch data publication of affected lines through its DR site. Data for all remaining unaffected lines to continue to be published out of Production site. | Data flow for affected output lines will resume from the DR source subnet - Note: Subscribers can continue to send retransmission requests to their Production input retransmission lines. Any retransmission of data for the affected lines will be disseminated over the retransmission lines from DR source subnet
7 | 10:30:00 - 11:00:00 AM | Complete site Failover from Production to DR | OPRA | Pillar OPRA to simulate Production site failure | - Disconnection of all OPRA Input and Retransmission lines connected to OPRA on both Production and DR site - Disruption in output multicast data dissemination for all lines
|  |  |  | Pillar OPRA to failover to DR site and publish following messages: 1) Reset Block Sequence Number (Category H Type K) for each OPRA output line to reset to sequence number 1 2) Disaster Recovery Data Center Activation (Category H Type P) message 3) Zero Quotes (Quote messages with Zero Price and Size) on behalf of all participants across all symbols | Subscribers to receive and process sequence reset message disseminated from the DR site Note - To request retransmission for any range of messages disseminated after the sequence reset to 1, Data Subscriber would be required to apply the offset up to 4,294,967,295 in the message sequence number
|  |  |  | Pillar OPRA to enable OPRA Input and Retransmission lines of the DR site | DR Input IP/Ports available to establish connections
|  |  | Participants | Participants to reconnect to OPRA on their Input IP/Ports on Pillar OPRA DR site and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence numbers, as previously processed over the Production site
|  |  |  | Participants to start submitting Quote and Trade data from the latest Sequence Numbers | Quotes and trades accepted and disseminated on the output lines. Subscribers can request retransmission for any gaps via the retransmission lines on the DR site
8 | 11:00:00 AM - 12:30:00 PM | Network Failure in DR | OPRA | Pillar OPRA to simulate Network Failure scenarios on DR site which may result in - - Failure of a subset of OPRA Input lines for participants - Momentary disruption in output multicast data dissemination | - Some Participant may see Primary input lines disconnected - Subscribers may see a momentary outage in data flow on the output lines and can request retransmission for the gap
|  |  | Participants | In case of a line disconnection, Participants to reconnect to OPRA to their backup connection on DR site. Participants to reestablish sequence numbers and continue submitting Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
9 | 12:35 |  |  | End of Test
Configuration after conclusion of Industry Non-Functional Test
10 | 12:35 | Operating out of DR from Monday 5/24 to Friday 5/28 |  | Starting Monday, May 24, Pillar OPRA will operate out of DR for a week, till Friday, May 28 | All Participants and data Subscribers shall ensure that any required configurations on their end are in-place to submit and receive data through the DR Input connections will only be allowed on the DR Site and data will be disseminated from the DR source subnet for same subset of multicast addresses as planned for the parallel phase (Regular Hours Multicast Lines: Line 1, Line 2, Line 3 & Line 4 and Extended Hours Multicast Lines: Line 97, Line 98, Line 99 & Line 100)