## OPRA GTH Test Plan - Oct 16
OPRA Global Trading Hours (GTH) - Testing Checklist
Participant/Subscriber:
Contact Name:
Contact Email:
Contact Phone#:
# | Time | Test Category | Action By | Test Description | Expected Results | Tested? ( Y, N, N/A ) | Participant Comments
Hourly Test Plan
Friday, October 15
1 | 7:45:00 PM - 8:30:00 PM | SOD | OPRA | OPRA Global Trading Hours (GTH) to trigger Start of Day message
2 | 7:45:00 PM - 6:00:00 AM | Participant Connectivity | CBOE | CBOE to establish connectivity for Primary Input IP/Ports on OPRA GTH Note - CBOE must also connect to OPRA for Extended Trading Hours (ETH) Sessions upon OPRA Start of day on Saturday, September 18 | CBOE to establish connection to OPRA GTH
|  |  |  | Cboe can start to submit Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
Saturday, October 16
3 | 6:00:00 - 6:15:00 AM | Network Failure | OPRA | OPRA GTH to simulate Network Failure scenarios which may result in - - Failure of a subset of OPRA Input lines for CBOE - Momentary disruption in output multicast data dissemination | - CBOE will see Primary input lines disconnected - Subscribers may see a momentary outage in data flow on the output lines and can request retransmission for the gap
|  |  | CBOE | In case of a line disconnection, CBOE to reconnect to OPRA and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence number via Block Sequence Number Status Response Message (Category N Type M)
|  |  |  | CBOE to resume submitting Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
4 | 6:15:00 - 6:30:00 AM | Single Participant Line Disconnect | OPRA | OPRA GTH to simulate Input Port failure of a subset of OPRA Input lines for CBOE | CBOE will see some Primary input lines disconnected
|  |  | CBOE | For the affected lines, CBOE to reconnect to OPRA on their backup lines and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence number via Block Sequence Number Status Response Message (Category N Type M)
|  |  |  | CBOE to resume submitting Quote and Trade data via their backup connections | Quotes and trades accepted and disseminated on the output lines
5 | 6:30:00 - 6:45:00 AM | Double Participant Line Disconnect (with Sequence Number Jump) | OPRA | OPRA GTH to simulate Input Port failure on both Primary and Secondary OPRA lines for CBOE | CBOE cannot connect to OPRA
|  |  |  | OPRA GTH to simulate a sequence number jump on subset of OPRA Input lines and recover Primary and Backup lines for CBOE | Input lines available for reconnection
|  |  | CBOE | CBOE to reconnect to OPRA and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence number via Block Sequence Number Status Response Message (Category N Type M)
|  |  |  | CBOE to resume submitting Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
6 | 6:45:00 - 7:00:00 AM | Output Multicast Sequence Reset | OPRA | OPRA GTH to simulate a sequence number jump on subset of OPRA multicast lines and publish Reset Block Sequence Number (Category H Type K) message | Subscribers to receive and process sequence reset message
|  |  |  | OPRA GTH to continue publishing subsequent Quote and Trade messages from the updated output sequence number | Subscribers to receive data and process the sequence number increase. Note - This is not an actual gap that can be retransmitted
7 | 7:00:00 - 7:15:00 AM | Output Publication Primary Process Failure | OPRA | OPRA GTH to simulate Primary Output Publication process failure. Data Publication to switch to backup process | Subscribers may see a momentary outage in data flow on the output lines. Subscribers can request retransmission for the gap
8 | 7:15:00 - 7:45:00 AM | Input Line Subsystem Failure | OPRA | OPRA GTH to simulate Input line subsystem failure which impacts Primary and Backup connections for CBOE input lines | - Disconnection of all Input and Retransmission lines for CBOE - OPRA to publish Zero Quotes for all symbols
OPRA GTH to restore input connectivity for CBOE on Production Site
|  |  | CBOE | CBOE to reconnect to OPRA and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence number that was processed prior to failure, via Block Sequence Number Status Response Message (Category N Type M)
|  |  |  | CBOE to resume submitting Quote and Trade data | Quotes and trades accepted and disseminated over the output lines
9 | 7:45:00 - 8:00:00 AM | Partial site Failover from Production to DR for output Multicast lines | OPRA | OPRA GTH to simulate partial failure of Output Publication process which will disrupt data flow for a subset of multicast output lines | - No impact to CBOE, they shall continue to send messages on the input lines on which they are connected to - Subscribers would see an outage in data flow on the affected output lines
|  |  |  | OPRA GTH to switch data publication of affected lines through its DR site. Data for remaining unaffected lines to continue to be published out of Production site. | Data flow for affected output lines will resume from the DR source subnet - Note: Subscribers can continue to send retransmission requests to their Production input retransmission lines. Any retransmission of data for the affected lines will be disseminated over the retransmission lines from DR source subnet
10 | 8:00:00 - 8:30:00 AM | Complete site Failover from Production to DR | OPRA | OPRA GTH to simulate Production site failure | - Disconnection of all OPRA Input and Retransmission lines connected to OPRA on both Production and DR site - Disruption in output multicast data dissemination for all lines
|  |  |  | OPRA GTH to failover to DR site and publish following messages: 1) Reset Block Sequence Number (Category H Type K) for each OPRA output line to reset to sequence number 1 2) Disaster Recovery Data Center Activation (Category H Type P) message 3) Zero Quotes (Quote messages with Zero Price and Size) on behalf of CBOE across all symbols | Subscribers to receive and process sequence reset message disseminated from the DR site Note - To request retransmission for any range of messages disseminated after the sequence reset to 1, Data Subscriber would be required to apply the offset up to 4,294,967,295 in the message sequence number
|  |  |  | OPRA GTH to enable OPRA Input and Retransmission lines of the DR site | DR Input IP/Ports available to establish connections
|  |  | CBOE | CBOE to reconnect to OPRA on their Input IP/Ports on OPRA GTH DR site and establish sequence numbers by sending Block Sequence Number Status Inquiry Request Message (Category N Type L) | OPRA to accept input connections and respond with latest sequence numbers, as previously processed over the Production site
|  |  |  | CBOE to resume submitting Quote and Trade data from the latest Sequence Numbers | Quotes and trades accepted and disseminated on the DR output lines. Subscribers can request retransmission for any gaps via the retransmission lines on the DR site
OPRA GTH to recover Production site for redundancy
11 | 8:30:00 - 9:00:00 AM | Complete site Failover from DR to Production | OPRA | OPRA GTH to perform another site failure and switch back from DR to Production (OPRA GTH to repeat steps in test #10) | Disconnection of all OPRA Input and Retransmission lines, and, Disruption in output multicast data dissemination for all lines in DR
|  |  | CBOE | CBOE to reconnect to OPRA GTH on the Production site, reestablish sequence numbers and continue submitting Quote and Trade data | Quotes and trades accepted and disseminated on the Production output lines
12 | 9:15 | EOD | OPRA | OPRA GTH to trigger End of Day message