## OPRA GTH Test Plan - Nov 6
OPRA Global Trading Hours (GTH) - Testing Checklist
Participant/Subscriber:
Contact Name:
Contact Email:
Contact Phone#:
# | Time | Test Category | Action By | Test Description | Expected Results | Tested? ( Y, N, N/A ) | Participant Comments
Hourly Test Plan
Friday, November 5
1 | 7:45:00 PM - 8:30:00 PM | SOD | OPRA | OPRA Global Trading Hours (GTH) to trigger Start of Day message
2 | 7:45:00 PM - 6:00:00 AM | Participant Connectivity | CBOE | CBOE to establish connectivity for Primary Input IP/Ports on OPRA GTH Note - CBOE must also connect to OPRA for Extended Trading Hours (ETH) Sessions upon OPRA Start of day on Saturday, November 6 | CBOE to establish connection to OPRA GTH
|  |  |  | CBOE can start to submit Quote and Trade data | Quotes and trades accepted and disseminated on the output lines
Saturday, November 6
3 | 6:00:00 - 9:15:00 AM | Data Verification | CBOE | CBOE to submit applicable messages to both OPRA and OPRA GTH | - Messages from OPRA GTH published with Session Indicator 1 - Messages from OPRA ETH published with Session Indicator X - Data Subscribers to process multicast data from OPRA GTH
|  |  | Subscribers | Data Subscribers can send Retransmission request to Pillar OPRA | Data Subscribers can confirm requested data on the retransmission channel
4 | 9:15 | EOD | OPRA | OPRA GTH to trigger End of Day message