## Template Instructions
Template Instructions
(Instructions for each line are hidden in column A. Just click on the cell and read the text in the formula bar.)
1. TIMING: To begin, simply enter your start date in cell 3E and the rest of the dates will auto-populate with default suggestions to help you anticipate the timing. The dates are calculated to relate to each other based on assumptions of how long it will take to complete each task. You can edit the start and end dates directly or by editing the cell formula.
2. TASKS: Edit tasks required to meet your organisational needs. If you delete rows when removing tasks, you may need to input a new start or end date for subsequent tasks that were connected to that timing. Determine which prior date your task depends on and in the “Start” cell for that task you can link it to the relevant date. For example, if you delete the task row “Announcement to managers”, the start date for the “Organization wide announcement” will say #REF!. Go to the start cell for that line type in = and click on the relevant date (perhaps the end date for the communication plan) and hit enter. You should then see recommended dates repopulate.
3. RESPONSIBILITIES: We recommend a list of project team members below and suggest who may "own" each task. For each cell in column C there is an arrow you can click with a drop down menu.
RESPONSIBILITY
(Feel free to edit or delete rows below; you can use team member names rather than department. If you need to add a team member, we suggest you insert a row between 11 and 19. If you add it to the end of the list you will have to reprogram the validation.)
Pulsely
Project Mgr
Pulsely + Project Mgr
Project Team
Legal
IT
Communications
Business Leaders
D&I Owner

## ProjectSchedule
Pulsely Diversity & Inclusion Project
Enter Company Name in cell B2. | Project Manager
Enter the name of the Consultant,if appropriate, in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | Project Start: |  | 2020-09-02
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2020-08-31 | [6 empty] | 2020-09-07 | [6 empty] | 2020-09-14 | [6 empty] | 2020-09-21 | [6 empty] | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-08-31 to 2021-04-22
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-08-31 to 2021-04-22
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Preparation Phase |  |  |  |  | #VALUE!
Cell B9 contains the sample task "Task 1." Cell E9 equals cell E3 the Project Start Date. All other dates will calculate automatically from there as a default starting point. | Host your Internal Project Launch Meeting STEP 2 GUIDE (link) |  | 0% | 2020-09-02 | 2020-09-07 | 6
| Address GDPR Concerns | Legal | 0% | 2020-09-02 | 2020-09-10
Rows 10 through 19 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Build your Project Plan and update responsibiltiies STEP 3 GUIDE (link) | Project Mgr | 0% | 2020-09-03 | 2020-09-08
| Finalize Communication Plan STEP 4 GUIDE (link) | Project Mgr | 0% | 2020-09-05 | 2020-09-10
| Announcement of Project from Sr Leader to Line Managers (TEMPLATE A) | Communications | 0% | 2020-09-07 | 2020-09-10
| Define organisational data needs and cuts (Regions, Function, etc) | Pulsely + Project Mgr | 0% | 2020-09-07 | 2020-09-09 | 3
| Finalize survey decisions (e.g., demographics) STEP 5 GUIDE (link) | Pulsely + Project Mgr | 0% | 2020-09-09 | 2020-09-12 | 4
| Upload HR data to Pulsley (If needed) | Project Mgr | 0% | 2020-09-10 | 2020-09-20 | 11
| Program Dashboard | Pulsely | 0% | 2020-09-10 | 2020-09-15 | 6
| Organization-wide Announcement of Project from Sr Leader (TEMPLATE B) | Communications | 0% | 2020-09-12 | 2020-09-19
| Review Dashboard Guidance STEP 6 GUIDE (link) | Project Mgr | 0% | 2020-09-15 | 2020-09-20 | 6
| Review D&I infrastructure guidance | Project Mgr | 0% | 2020-09-14 | 2020-10-05 | 22
The cell at right contains the Phase 2 title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Collect Data
| Pre-Test Survey STEP 7 GUIDE (link) | Pulsely + Project Mgr | 0% | 2020-09-17 | 2020-09-19
| Send out Survey Link via email (TEMPLATE 1) | Pulsely + Project Mgr | 0% | 2020-09-24 | 2020-09-26 | 3
| Compare Response rate to population | Pulsely + Project Mgr | 0% | 2020-09-26 | 2020-10-06
| Send out reminder (TEMPLATE 2) | Pulsely + Project Mgr | 0% | 2020-10-01 | 2020-10-03 | 3
| Nudge from individual business leaders if necessary (TEMPLATE 3) | Business Leaders | 0% | 2020-10-04 | 2020-10-06 | 3
| Send out Final Reminder (TEMPLATE 4) | Pulsely + Project Mgr | 0% | 2020-10-07 | 2020-10-08 | 2
Phase title block | Uncover Insights
| Schedule review session with Leadership team | Project Mgr |  | 2020-10-09 | 2020-10-16 | 8
| Cleaning Data (if necessary) | Pulsely |  | 2020-10-09 | 2020-10-12 | 4
| Analyzing Data | Pulsely |  | 2020-10-12 | 2020-10-19 | 8
| Send out Post-Survey Thank you (TEMPLATE 5) | Project Mgr |  | 2020-10-15 | 2020-10-18
| Interpretation of Results | Pulsely |  | 2020-10-19 | 2020-10-27
| Produce Report | Pulsely |  | 2020-10-27 | 2020-11-03
| Initial Review Report and results STEP 8 GUIDE (link) | Pulsely + Project Mgr |  | 2020-11-03 | 2020-11-08 | 6
| Facilitate session with Leaders to identify key priorities STEP 9 GUIDE (link) | Project Team |  | 2020-11-11 | 2020-11-25 | 15
| Leaders to establish ownership and Accountability in Organization | Business Leaders |  | 2020-11-11 | 2020-11-25 | 15
| Leadership Message: Highlights of results (TEMPLATE C) | Communications |  | 2020-11-25 | 2020-11-30 | 6
Phase title block | Take Action
| Define Action Plan and Next Steps STEP 10 GUIDE (link) | Project Team |  | 2020-11-26 | 2020-12-06 | 11
| Review Best Practices and choose iniatives to implement | Project Mgr |  | 2020-12-06 | 2020-12-11 | 6
| Assign accountability for implementation and results | Project Team |  | 2020-12-11 | 2020-12-16 | 6
| All-organisation announcement (TEMPLATE D) | Communications |  | 2020-12-16 | 2020-12-23 | 8
| Individual Leader All-hands session (if possible) | Business Leaders |  | 2020-12-23 | 2020-12-30
| Implement Initiatives | D&I Owner |  | 2020-12-16 | 2021-04-15
| Engage employee networks (if appropriate) | D&I Owner |  | 2020-12-16 | 2021-01-13
Refine
| Collect Ongoing Pulsely Data to monitor inclusion and progress | Pulsely + Project Mgr |  | 2020-12-03 | 2020-12-24 | 22
| Evaluate and Refine strategies where necessary | D&I Owner |  | 2020-12-24 | 2021-01-07 | 15
| 6-month survey to monitor progress | Pulsely + Project Mgr |  | 2021-03-23 | 2021-04-06 | 15
| Next stage strategy development | D&I Owner |  | 2021-04-06 | 2021-04-20 | 15