## 10 months
BASF -- COUNT DOWN |  |  | 10 Months
Completed? | Who? | What? | Notes
Review evaluations from prior events (if possible) in order to determine what worked well and what could improve
Sponsors: reaching out, getting commitments
Confirm committment of major sponsor(s)
Exhibitors: reach out to those who want to commit early
Confirm date of event
Confirm venue
Letter sent to local officals
Identify other events that we might attend for promotion
Confirm/define job descriptions of planning committee members
Public relations: contact politicians to include in their communications

## 6 months
BASF -- COUNT DOWN |  |  | 6 months
Completed? | Who? | What? | Notes
Research and identify potential content provders
Begin reaching out to all

## 4 months
BASF -- COUNT DOWN |  |  | 4 months
Completed | Who? | What? | Notes
Exhibitor map to scale with booth layout
Finalize Public Relations plan
Design ads
Translate ads if necessary
Write press releases
Determine banner and poster needs
Order banners and posters
Determine online needs: websites, Twitter, Facebook, sponsor lists
Update website
Sponsors committed for ad space
Communicate with County Library regarding event details
Dignitaries invited to be signatures on letter
Dates in all local Patch as events
Info to Spanish-speaking stations
Finalize contracts
Discuss logistical details with venue
Determine Wi-fi availability
Recruit food vendors

## 3 months
BASF -- COUNT DOWN |  |  | 3 months
Completed | Who? | What? | Notes
Promote event at Air Fair at Sonoma Airport
Send flyer to county school board for approval
Connect with Sonoma County Science Office of Education
Connect with Santa Rosa City Schools

## 2 months
BASF -- COUNT DOWN
Completed? | Who? | What? | Notes
Volunteer job descriptions reviewed
Logistics confirmed with Sonoma County Fairgrounds
More food vendors
|  | Identify signage needs. | Consdider: Restrooms, parking, photography disclaimer, welcome, thank you, show times and festival branding (flags, banners, etc)
Exhibit layout organized and coming together
Visit local schools
E-mail Discovery Day “save the date” to teachers/schools
Preliminary press releases mailed out
Begin recruiting volunteers

## 4 weeks
BASF -- COUNT DOWN |  |  | 4 weeks
Completed? | Who? | What? | Notes
Review contract with Fairgrounds for any additional items
|  | Order booth/exhibit hall dividers | tenting or pipes/drapes
Order tables and chairs
Order recycling containers and trash cans
Submit event to radio community service announcements
Signage completed and ordered
Exhibitors committed
Volunteers identified and confirmed
Print fliers for schools
Host "flier packaging party"
Determine delivery routes for flier distribution
Fliers delivered to schools
Email DD information to teachers, schools
Order lab coats for event volunteers and staff
Order table covers for exhibitors
Attendee evaluations printed
Exhibitor evaluation printed
Arrange photographer
Information to radio stations
Submit all necessary permits to city and/or county

## 2 weeks
BASF -- COUNT DOWN |  |  | 2 weeks
Completed? | Who? | What? | Notes
Submit exhibitor floorplan to venue
Submit exhibitor floorplan to city (fire dept, etc.)
Run ad in Sunday Paper
Confirm email to all exhibitors
Confirm email to all volunteers
Lock down map details for printing
Print booth signage (organization and activity title)
Prepare Tool Kit (see list below)
Tool Kit
Garden hose
Duct tape
Blue masking tape
Wire
Wire clipper
Hammer
Screw drivers of various types
Extension cords
Pliers
String
Cord
Band-aids (separate from First Aid kit)
Bungie cords (12)
Bucket
Umbrellas (if weather necessary)
Sponge
Rubber gloves
Box cutter
Ladders
Staple gun
Staple gun staplers
Hand soap
Gardening gloves
Nametags

## 1 week
BASF -- COUNT DOWN
Completed? | Who? | What? | Notes
Confirm map and program
Print exhibitor evaluations and attendee evaluation forms
Locate and/or purchase hospitality room supplies (see below)
Schedule volunteers
Purchase needed activity supplies
Print and glue exhibitor ID signs
Print photo release notices, volunteer job descriptions, and schedules for the Hospitaltiy Room
FOOD ITEMS for HOSPITALITY ROOM
3 gallons orange juice
small muffins
coffee
snacks (cookies, energy bars, chips, etc)
waters
plastic cups
coffee cups
cream/sugar
SUPPLIES FOR HOSPITALITY ROOM
Tool kit
"I talked to a Scientist" buttons
Evaluation sheets
Food and water
Coffee maker(s)
Walkie talkies - charged
Stapler
Staples
Sharpies
Scissors
Clip boards
Paper stapler and staples
Staple remover
Push pins or tacks
Camera -- charged
$300 cash in $10 for lunches
Push brooms and dust pans for cleanup
Attendance clickers

## 1 day
BASF -- COUNT DOWN |  |  | Day Before
Completed | Who? | What? | Notes
Run Friday ad in local paper(s)
Charge walkie talkie and camera batteries
Print out Volunteer work schedule for leaders and one wall copy
10-5 pm: Visit venue and place table IDs
Prep signs and hang where possible
Post booth signage
Set up wi-fi
Distribute table cloths
Final walk through

## Day of Event
BASF -- COUNT DOWN |  |  | Event Day
Completed? | Who? | When? | What?
|  | 6:45 | Facility opens
|  | 7:00 | Prep for exhibitors
|  | 7:00 | Set out street signs
|  | 7:30 | Open for exhibitors
|  | 8:00 | Lab coats come up with Kishore to STAFF ROOM
Must unload at roll-up doors
Use carts to deliver supplies to booth area
Set up STAFF ONLY room for hospitality to vendors/exhibitors
Special exhibitor parking lot available
|  | 10:00 | Sign off with Fire Marshall
|  | 10:30 | All exhibitors ready to go
|  | 10:30 | Volunteer outside helping direct early arrivers
|  | 10:30 | Volunteer counters at gates
|  | 10:30 | Information booths ready
|  | 10:50 | Gates open to public
|  | 11:00 | Event begins!
|  | NOTE | Take more photos (everyone!)
|  | 3:00 | Distribute Exhibitor Evaluations
|  | 3:45 | Bring back directional signs from street
|  | 4:00 | Collect Exhibitor Evaluations
|  | 3:45 | Prep volunteers to organize vehicles, carts, and exhibitor pick up
|  | 4:00 | Event ends; breakdown of exhibits
Exhibitors to remove all items they brought
Volunteers to help with clean up
Remove all signs on walls
Pick up trash in rooms and outside area
Dismount poster boards from A-frames; save for next year
|  | 4:45 | Close Hospitality Room
|  | 6:00 | All exhibitors and staff off property
CB
| CAT | Box with printed forms
| CAT | Sign
| CAT | Box for art supplies
| CAT | Box for completed artwork
| CAT | Art tools from Cat Nam
| CB | Stamps for art work
| CB | Ink pads for art work

## Post Event
BASF -- COUNT DOWN |  |  | Post Event
Completed | Who? | What? | Notes
Compile evaluations
Hold debrief meeting to go over evaluations and lessons learned
Write thank you notes
Determine art contest winners
Send prizes and certificates
Post scans of winners on website
Pay all outstanding invoices
Celebrate!
SET DATE FOR NEXT YEAR