Sample Science Festival Production Timeline

Organizing a festival in 12 months

This timeline maps out some of the tasks typically involved in organizing a large-scale science festival. While it is adopted from planning documents from large-scale science festivals in Cambridge and San Diego, tasks and timelines vary significantly from festival to festival—and even somewhat from year to year.

Before you start

- Establish general festival goals and articulate a clear and inclusive vision

- Know how the festival will be administered (perhaps an existing nonprofit has agreed to handle financials and insurance, to house staff, and assist with fundraising)

- Contact the Science Festival Alliance and become a member, visit other science festivals, and meet with other organizers

- Hire staff or appoint management/leadership

- Create a broad budget estimate

- Determine scope of festival and region served

- Carefully choose a name for the festival

12 months out

Fundraising and collaborations:

- Develop a fundraising plan and structure (for example: size of gift required for title sponsorship)

- Meet with potential lead donors and major collaborators (this activity will continue throughout the planning phase)

- Establish guidelines for Advisory Board and Steering Committee, appoint chairs for each, and extend invitations for members (engaging committee members will continue throughout planning phase)

11 months out

Programming:

- Set up basic structure of the festival (for example: an 8-day celebration with large family-friendly capstone events on the weekends, school programming on weekdays, and adult programs on three evenings)

- Establish procedure for soliciting and accepting events, activities, and exhibits from collaborators

- With collaborators, brainstorm events and activities that will become signature programs

Marketing:

- Select and meet with designer to begin creating logo and signature materials

- Set up basic website and social media platforms

Logistics:

- Establish initial detailed budget

- Confirm dates of the festival

- Reserve venues

- If the festival’s main events are expected to be very large, also:

  - Confirm and finalize contracts with managing consultant as necessary

  - Obtain insurance

  - Begin physical layout with traffic plan to determine true capacity of event

  - Determine needed contractor services and issue RFP (for example: tents, electrical, security, trash, cleaning, etc.)

  - Determine what permitting processes may be required

10 months out

Logistics/administration:

- Confirm and finalize contracts with all consultants (including independent evaluators) as needed

Marketing:

- Develop marketing plan that includes ad buys, in-kind media sponsorships, save-the-date announcements, and festival schedule distribution

- Take action on any long-lead marketing (for example: reserve city pole banner sites)

Programming/collaborators:

- Draft “call for entries” form and guidelines (including best practices and any fee structure for festival participation), and begin distribution to potential collaborators

- Determine main signature programs with major collaborators and begin making necessary arrangements

- Review planned festival schedule to confirm broad array of activities that will serve all desired audiences

9 months out

Fundraising:

- Incorporate marketing plan into sponsor opportunities (for example, size of gift required to receive logo placement in ad buys)

- Potential lead sponsors close to decision

Programming/collaborators:

- Continue to recruit additional festival collaborators and exhibitors at all levels, including individual scientists and engineers

8 months out

Marketing:

- Begin regular marketing meetings

- Write and distribute long-lead press releases

Programming:

- Formalize connections with K-12 school systems

7 months out

Marketing:

- Determine all major printed materials and begin design (for example: signage, festival program, special flyers, etc.)

- Prepare online platform for festival schedule of events

Logistics:

- Begin recruiting festival volunteers

6 months out

Marketing:

- Publicly launch science festival website

- Send out save-the-date postcards or other materials

- Begin promoting festival by sending volunteers to public events (for example, with a booth at a farmers market)

- Book photographer and/or videographer

Programming:

- Launch any long-lead signature programs (for example: student contests)

- Schedule any festival programming that will take place at community venues (schools, libraries, etc.)

Logistics:

- Fine-tune estimate of audience for main and signature events, adjust budget accordingly

- Select main event contractors and hold initial meetings with them

5 months out

Programming/collaborators:

- Call for entries deadline for collaborators

Logistics:

- Create plan for evaluating the success of the festival

4 months out

Programming/logistics:

- Carefully review activities proposed by collaborators through call for entries system

- Clarify participation with each collaborator, working with each to fine-tune all details regarding the event or exhibit proposed, including descriptive wording for the festival program

3 months out

Fundraising:

- Finalize arrangements with all donors

Marketing:

- Deadline for including new events, activities, and sponsors in festival program

- Design of print and web-based festival program gets under way

Logistics/administration:

- Conduct on-site meetings with all event contractors for main event and/or large, signature events

- Develop volunteer plan and staffing plan to ensure that all festival elements have adequate staffing and representation

- Make final adjustments to budget to reflect actual funds raised; leave a remainder for the following year

2 months out

Logistics:

- Create event planning grid organizing all events and roles for participants; distribute to each individual on festival team

- Create a detailed rain plan for each festival event

Marketing:

- Print major signage

- Distribute all printed materials, including festival program

- Long-lead marketing in place (street banners up, etc.)

Programming:

- Send invitations to all sponsors and major collaborators for VIP recognition event (for example: a special lunch during the festival main event, or a dinner beforehand)

- Hold training sessions for festival collaborators, including exhibitors at main event

Final month before festival

Logistics:

- Confirm all event details with all participants

- Confirm event layout for main event

- Confirm all venues

- Hold training sessions for volunteers and any temporary staff

- Begin watching weather predictions compulsively, try to get enough sleep

Marketing:

- Make final marketing push and distribute all promotional materials

Post-festival

Collaborators/fundraising

- Send thank you/success letter to all donors and collaborators

- Wrap-up post-production meetings with donors, collaborators, evaluators, and key consultants/contractors

Logistics:

- Finalize previous year’s budget

- Conduct internal event review

- Begin planning for next year!