## How To Use
Instructions
Event Project Plan Template
The Event Project Plan Template provides a real time overview when key items are due. A template should be used for each event you oversee. The first thing you should do is to change the finish date to the date of your event. The template is setup for a 6 mths planning cycle. Feel free to adjust the weeks out as needed.
Event Plan Timeline
The Event Plan Timeline provides a 6-12 month planning process for events. You may not have to use all of these items for your events. Please customize for each event.

## Event Project Plan Template
Church Event Project Plan Template/Task List |  |  |  | Finish Date: | 2021-06-01 | <--Change this to the day of your event
Event Name, Dates |  |  |  | # of Days per Week: | 7
Task Description | Deadline (X weeks out)* | Deadline Date** (do not change) | Assigned To
PROJECT MANAGEMENT TASKS:
Assign point person for each department | 24 | 2020-12-15
Create master timeline | 24 | 2020-12-15
Set-up project management application (Excel, Asana, Trello, etc) | 24 | 2020-12-15
Schedule planning meetings | 23 | 2020-12-22
Plan for all needed reports (attendence, volunteers, revenue) | 23 | 2020-12-22
Plan regular updates to senior leadership | 23 | 2020-12-22
Facilitate Lessons Learned Session | -2 | 2021-06-15
ALL DEPARTMENTS TASKS:
Get budget approval | 24 | 2020-12-15
Submit Purchase Requests | 12 | 2021-03-09
Assign all tasks with due dates | 22 | 2020-12-29
Send volunteer needs to Volunteer Team | 12 | 2021-03-09
Create supply list | 10 | 2021-03-23 | Contact Office Manager
Get supplies (If mnistry/office supplies contact Office Manager) | 8 | 2021-04-06
Send moneybag / credit card requests to Finance Team (to make change at day-of registration, merchandise, & food) | 8 | 2021-04-06
Schedule volunteer training | 8 | 2021-04-06
MARKETING TASKS: |  |  | Comm & Mktg
Complete announcement request | 12 | 2021-03-09
Design Graphics | 8 | 2021-04-06 | Comm & Mktg
- For print | 8 | 2021-04-06 | Comm & Mktg
- For web | 8 | 2021-04-06 | Comm & Mktg
Decide on phone number/website to use in promo materials | 8 | 2021-04-06 | Comm & Mktg
Design website and/or registrtion portal | 8 | 2021-04-06 | Comm & Mktg
Finalize graphics | 6 | 2021-04-20 | Comm & Mktg
For print (bulletin/invite card) | 6 | 2021-04-20 | Comm & Mktg
For website & social | 6 | 2021-04-20 | Comm & Mktg
For projector screens | 6 | 2021-04-20 | Comm & Mktg
Create and finalize online & print registration pieces | 6 | 2021-04-20 | Comm & Mktg
Post to Eventbrite |  |  | Comm & Mktg
Post to Evensi |  |  | Comm & Mktg
Post to Facebook Events |  |  | Comm & Mktg
Design and schedule social media posts | 4 | 2021-05-04 | Comm & Mktg
Design and schedule Facebook Ads | 4 | 2021-05-04 | Comm & Mktg
Create promotional videos | 3 | 2021-05-11 | Comm & Mktg
Give staff information to use for responding to phone calls/emails | 6 | 2021-04-20 | Comm & Mktg
Write Press Release | 8 | 2021-04-06 | Comm & Mktg
Send Press Release to new outlets | 6 | 2021-04-20 | Comm & Mktg
Send announcement to radio stations | 8 | 2021-04-06 | Comm & Mktg
Finalize signage | 4 | 2021-05-04 | Comm & Mktg
Add event to church bulletin and announcements | 4 | 2021-05-04 | Comm & Mktg
Email church members | 4 | 2021-05-04 | Comm & Mktg
Schedule radio and television interviews | 8 | 2021-04-06 | Comm & Mktg
Develop event participant/vendor survey | 4 | 2021-05-04 | Comm & Mktg
PRODUCTION TASKS:
Reserve venue and date | 24 | 2020-12-15 | contact Office Manager
Reserve church van | 20 | 2021-01-12 | contact Office Manager
Book musicians | 24 | 2020-12-15 | contact Minister of Music
Book speakers | 24 | 2020-12-15
Reserve audio equipment | 20 | 2021-01-12 | contact Comm & Mktg
Reserve video equipment | 20 | 2021-01-12 | contact Comm & Mktg
Reserve lighting equipment | 20 | 2021-01-12 | contact Comm & Mktg
Book A/V staff | 20 | 2021-01-12 | contact Comm & Mktg
Finalize setup- expected capacity, tables, chairs and linens | 12 | 2021-03-09 | contact Property Manager & Office Manager
Reserve decor | 12 | 2021-03-09
Schedule rehearsal times | 12 | 2021-03-09
Create a minute-by-minute schedule | 8 | 2021-04-06
Schedule full Run Through | 4 | 2021-05-04
Obtain speaker notes in advance | 4 | 2021-05-04
Finalize set list | 4 | 2021-05-04
Finalize minute-by-minute schedule | 3 | 2021-05-11
VOLUNTEERS TASKS:
Create a list of all volunteer roles needed | 22 | 2020-12-29
Write volunteer job descriptions | 22 | 2020-12-29
Determine number of volunteers needed for each role | 22 | 2020-12-29
Create recruiting plan | 20 | 2021-01-12
Create and finalize sign-up process (online and/or paper) | 12 | 2021-03-09
Create volunteer registration process | 12 | 2021-03-09
Determine volunteer training process | 14 | 2021-02-23
Communicate all event information to volunteers | 12 | 2021-03-09
Train volunteers | 2 | 2021-05-18
Hold final volunteer training session; finalize assignments | 1 | 2021-05-25
Send thank you notes to volunteers | -1 | 2021-06-08
Create & send survey to volunteers | -1 | 2021-06-08
Reconfirm refreshments/meal schedule for volunteers | 0 | 2021-06-01
Set up checkin/intake area | 0 | 2021-06-01
CHILDCARE TASKS:
Decide whether to provide childcare | 23 | 2020-12-22
Decide on cost for childcare | 18 | 2021-01-26
Communicate cost for childcare to attendees and volunteers | 18 | 2021-01-26
Include way to gather information about childcare needs in registration process
Book childcare staff | 12 | 2021-03-09
Reserve rooms for childcare | 12 | 2021-03-09
Book children's activities | 8 | 2021-04-06
HOSPITALITY TASKS:
Find out food and beverage rules for the venue | 24 | 2020-12-15
Book hotel rooms | 24 | 2020-12-15
Map out food and beverage stations | 20 | 2021-01-12
Green Room
Staff
Attendees
Volunteers
Reserve vehicles to transport speakers/musicians | 12 | 2021-03-09
Book drivers | 8 | 2021-04-06
Send ryder to speaker | 8 | 2021-04-06
Confirm hotel room | 3 | 2021-05-11
SECURITY TASKS:
Determine who needs a background check | 20 | 2021-01-12 | Contact Deacon Cox
Plan emergency protocols | 20 | 2021-01-12
Book paid security | 12 | 2021-03-09 | Contact Deacon Cox
Communicate security procedures to all event staff/volunteers | 12 | 2021-03-09
Create plan for lost children | 12 | 2021-03-09
Book Ambulance / First Aid station | 12 | 2021-03-09
PARKING TASKS:
Secure permits for road closures | 22 | 2020-12-29 | Contact Property Manager
Map out parking layout | 20 | 2021-01-12 | Contact Property Manager
Reserve golf carts | 12 | 2021-03-09
Purchase signage | 12 | 2021-03-09 | Comm & Mktg
Reserve parking cones | 4 | 2021-05-04 | Contact Property Manager
EVENT HOSTS TASKS:
Create and distribute driving directions to attendees/staff/volunteers | 22 | 2020-12-29
Map out check in process | 16 | 2021-02-09
Map out Greeter stations | 16 | 2021-02-09
Map out restrooms for public / non-public use | 16 | 2021-02-09
Create plan for lost and found | 16 | 2021-02-09
Reserve crowd control barriers | 12 | 2021-03-09
Reserve attendance hand tally counters | 12 | 2021-03-09
Create plan for donations | 12 | 2021-03-09
FACILITIES TASKS:
Determine venue for the event | 23 | 2020-12-22
Determine audio, visual, lighting needs | 18 | 2021-01-26 | Contact Comm & Mktg
Create set up & tear down plan | 8 | 2021-04-06
Create plan for keeping restroom clean and stocked | 4 | 2021-05-04 | Contact Property Manager
Create plan for cleaning before and after event | 4 | 2021-05-04
MINISTRY TASKS:
Choose follow-up books and materials | 8 | 2021-04-06
Select online follow-up method | 8 | 2021-04-06
Book prayer team | 4 | 2021-05-04
FINANCE / BUSINESS OFFICE TASKS:
Contact church insurance agent to determine if they require special coverage for this event | 20 | 2021-01-12 | Contact Property Manager
Set up event registration (online, etc.) | 18 | 2021-01-26
Book ushers | 8 | 2021-04-06 | Contact Usher Director
Decide how to receive offering(s) | 8 | 2021-04-06 | Trustee Ministry
Envelopes
Text to give
Online giving
Notes:
*Change the number of weeks out deadline as needed. Listed here are recommendations based on an event that is six months out.
**Do NOT change this column. These cells include a formula that calculate the Deadline Date based on what you have in the "Deadline (X weeks out)" column. Specifically, the formula takes the Finish Date minus the Deadline (#X weeks out) data. This tells you when the person in the "Assigned To" column should finish a task. He/she will have to determine how long it will take to complete the task to calculate a start date.
* available for download at www.shiloh-bc.org/eventplanning
Formulas:
Deadline Date** (do not change) = F1-([Deadline (X weeks out)*]*F2)

## Event Plan Timeline
Project Plan Timeline Overview
6-12 months before event |  | * responsible party
Task | Department/Ministry
Reserve location/venue (complete room request form) | * submit to Office Manager
Decide event purpose
Choose a theme
Decide on time and date (Confirm availability of time and date)
Appoint an event coordinator/program manager
Select team members/setup subcommittees
Create master timeline
Schedule planning meeting
Assign all tasks with due dates (Event Project Plan Template)
Get cost estimates (decorations, food, etc)
Review submitted budget (food, equipment, decorations, activities, etc) | * Review w/ Area Director & Associate Pastor
Update/finalize budget | * Ministry Leadership/Trustee Ministry
Invite VIPs
Create graphics | * Comm & Mktg
Set marketing schedule | * Comm & Mktg
Hire photographer | * Comm & Mktg
Investigate need for special permits | * Property Manager
Reserve church van | *Contact Office Manager
Invite VIPs
Book musicians | * Minister of Music
Book speakers | *See Executive Office for Ministers
Reserve hotel rooms | * Executive Office
Book AV Staff | * Comm & Mktg
Review audio, video & lightning needs | * Comm & Mktg
Create volunteer roles & descriptions
Determine who will need background check
Decide whether to provide childcare
3-6 months before event
Task | Department/Ministry
Secure permit & insurance | *Property Manager
Set menu with caterer
Get written confirmation of VIP participants riders/special needs
Create Supply List
Submit Requisitions and/or contract if outside venue
Submit announcement request to www.shiloh-bc.org/announcement
Build website/registration portal for event & for volunteers | * Comm & Mktg
Finalize print registration form | * Comm & Mktg
Finalize graphics-print/web/screens | * Comm & Mktg
Design & schedule social media posts | * Comm & Mktg
Design & schedule Facebook ads | * Comm & Mktg
Desing & order particpant/volunteer t-shirt | * Comm & Mktg
Design and order volunteer lanyards | * Comm & Mktg
Write press release | * Comm & Mktg
Finalize setup-expected size/ table,chairs & linen needs | * Office Manager & Property Manager
Schedule rehearsal times | * Minister of Music
Create volunteer registration process
Determine volunteer training process
Plan checkin process
Book ushers | *Usher Ministry
2 months before event
Task | Department/Ministry
Send press release | * Comm & Mktg
Send announcements to radio stations | * Comm & Mktg
Finalize signage | * Comm & Mktg
Subcommittees finalize plans
Review/finalize budget, task sheets, & timeline
Create setup & tear down plan
Schedule ushers | *Usher Ministry
Set up offering process (envelopes, online giving, text giving) | * Trustee Ministry
Get supplies | *Ministry & Office Manager
1 month before event
Task | Department/Ministry
Confirm staff for registion, greeting, etc.
Confirm program participants
Prepare welcome packets for VIP and key particpants/staff
Get enlarged site plan/room diagram, assign seats/tables | * Ministry/Comm & Mktg
Meet with all outside vendors, consultants to coordinate event
Review script/timeline
Confirm transportation schedules: airlines, trains, buses, cars, limos
Confirm hotel accommodations
1 week before event
Task | Department/Ministry
Meet with committees for last minute details
Hold final volunteer training session; finalize assignments
Final walk through
Day of the event
Task | Department/Ministry
Arrive early
Be sure VIPS are in place and have scripts
Reconfirm meal schedule/meal refreshment for volunteers
Check with volunteers to make sure all tasks are covered
Set up checkin/intake area
2 weeks after the event
Conduct debrief meeting/lessons learned with everyone who participated in conducting the event | Everyone
* available for download at www.shiloh-bc.org/eventplanning