## About Vergo
About Vergo
Vergo is a software built exclusively for construction companies to automate repetitive excel processes and enable real-time collaboration between accounting and field teams.
Head to getvergo.com to learn more.
Schedule Demo
To schedule a demo with a product specialist, email rich@getvergo.com

## Construction Calendar
Construction Calendar
Priority | Task | Status | Files | Start date | End date | Duration | % Complete | Assigned to | Dependencies | Notes
| Project Initiation | Completed |  | 2023-02-01 | 2023-02-09 | 8 | 100%
High | Define project scope and objectives | Completed | file | 2023-02-01 | 2023-02-04 | 3 | 100% | Rich
Medium | Set up project team and roles | Completed | file | 2023-02-03 | 2023-02-04 | 1 | 100% | Rich | Define project scope and objectives
High | Budget allocation and funding | Completed | file | 2023-02-04 | 2023-02-09 | 5 | 100% | Rich
| Site Preparation | In Progress |  | 2023-02-10 | 2023-03-01 | 19 | 58.33%
High | Site layout and marking | Completed |  | 2023-02-10 | 2023-02-14 | 4 | 100% | Mark
High | Clearing and excavation | In Progress | file | 2023-02-14 | 2023-02-24 | 10 | 75% | Mark | Site layout and marking | Weather conditions pushed us back
High | Utility connections | Delayed |  | 2023-02-24 | 2023-03-01 | 5 | 0% | Mark | Clearing and excavation
| Foundation and Framing | Not Started |  | 2023-03-05 | 2023-04-04 | 30 | 0%
High | Pour concrete foundation |  |  | 2023-03-05 | 2023-03-07 | 2 | 0%
High | Frame walls, floors, and roof |  |  | 2023-03-07 | 2023-03-21 | 14 | 0% |  | Pour concrete foundation
Medium | Install plumbing and electrical rough-ins |  |  | 2023-03-21 | 2023-04-04 | 14 | 0% |  | Frame walls, floors, and roof
| Roofing and Exterior |  |  | 0 | 0 | 0 | 0%
| Install roof materials | [5 empty] | 0%
| Exterior siding and insulation | [5 empty] | 0%
| Windows and doors installation | [5 empty] | 0%
| Interior Rough-Ins, Finishes and final touches |  |  | 0 | 0 | 0 | 0%
| Install HVAC and ductwork | [5 empty] | 0%
| Rough-in electrical and plumbing | [5 empty] | 0%
| Insulation and drywall installation | [5 empty] | 0%
| Project Closeout |  |  | 0 | 0 | 0
Formulas:
Start date = MIN([Start date, row below]:E10)
End date = MAX([End date, row below]:F10)
End date = IF(ISBLANK([Start date]),"",[Start date]+[Duration])
Duration = DATEDIF([Start date],[End date],"D")